Annexure- 2

Nehru Yuva Kendra Sangathan

Department of Youth Affairs

Programs, Activities, Numbers and Timeline of the

Project “Youth Participation “Catch The Rain, where it falls, when it falls” for Water Conservation

with support of National Water Mission, Ministry of Jal Shakti, Govt. of India

| S.No | Program | Activities | No. of Activities | Month |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | December 2020 | January 2021 | February 2021 | March 2020 |
| 1. | Sensitization of NYKS Officials | Orientation and sensitization of NYKS State Directors, Dy. Directors and District Youth Officers | 01 | 16th December, 2020 |  |  |  |
| 2. | National Level Launching | Address by Hon’ble Sh. Gajendra Singh Sekhawat, Minister of Jal Shakti Mantralya, Key Note Address by Sh. Kiren Rijiju, Hon’ble Minister of State(i/c), Ministry of Youth Affairs and Sports and Sh. Ratan Lal Kataria, Hon’ble Minister of State, Jal Shakti Mantralya and other dignitaries. | 01 | 21st December, 2020 |  |  |  |
| 3. | District Level Launching | By involving D.M./D.C./Collector and Public Representatives | 623 Programs (One in each District) |  | 623 Programs |  |  |
| 4. | Oath on Water Conservation | By District Youth Officer along with Youth Volunteers | 31,150 Oath Taking (one program each in 50 villages of all 623 Districts) |  | 31,150 Programs |  |  |
| 5. | Orientation and Motivation of Youth Leaders and Volunteers | Orientation and Motivation of Youth Leaders and Volunteers and establishing linkages | 3,115 Programs (5 Activities per District x 623 Districts) |  | 3,115 Webinars |  |  |
| 6. | Advocacy and Environment Building for participation and support for Water Conservation | PRIs, Opinion Leaders, Village Spokespersons and Volunteers, E-Posters, Banners and other publicity materials, Wall writing, on prominent places, e-slogans coverage in Print Media as well as Electronic Media and use of social media, Promotion of Tagline “Catch the Rain, where it Falls, when it falls” | 62,300 Programs (2 Programs in each village x 50 villages x 623 Districts) |  | 20,766 Programs | 20,768 Programs | 20,766 Programs |
| 7. | Awareness and Education | Awareness Campaigns, Prabhat Pheris, and Nukkad Nataks | 62,300 Programs (2 programs in each village x 50 villages x 623 Districts) |  | 20,766 Programs | 20,768 Programs | 20,766 Programs |
| 8. | Community Mobilization and Motivation | Personal Contact and social media outreach for motivating families/villagers to Catch the Rain where it Falls When it Falls at their Houses, Field and Village Common Lands | 31.15 Lakh Families (10 Members of a Youth Club in each village will mobilize 100 families in a village x 50 Villages x 623 Districts) |  | 10 Lakh | 10 Lakh | 11 Lakh |
| 9. | Water Talks and Dialogue | Talks and Dialogues with subject experts and motivators | 31,150 Programs (One program each in all 50 Villages x 623 Districts) |  | 9,345 Programs | 12,460 Programs | 9,345 Programs |
| 10. | Knowledge Competition | Quiz, Poster Making, Paintings and Slogan Writing | 3,115 Programs (One programs each on a cluster of 10 villages) |  | 1,557 Competitions | 1,558 Competitions |  |
| 11. | Community Work Camps on Voluntary basis | De-silting of water resources including traditional water bodies; Digging , maintenance and repairing of water tanks, wells, ponds; Construction of village level small check dams, etc. as per local need and sources. | 31,150 Programs (One program each in all 50 Villages x 623 Districts) in the mentioned categories & others |  |  | 15,575 Programs | 15,575 Programs |